## Overview
100 day plan
PURPOSE
To help make it happen. This illustrative plan will support you to implement the tools in this guide. It is designed to help you to assign roles and responsibilities and complete a 100 day plan, ensuring actions and responsibilities are clear and time bound. We have created an example 100 day plan which can be edited to fit differing timescales and differing project plans. This plan is not meant to be prescriptive, but to act as a template for individual organizations to build on.

## 100 day plan
Example 100 day plan
The below is an example of a project plan. Use the template and edit the actions, owners and timelines.
Action | Relevant tool | Owner | Week number
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1. Mobilize |  |  | Week number 1: Phase 1
Identify and mobilize the core change team | TOOL 4 CHANGE MANAGEMENT ROLES | CFO | bar: Week number 1
Confirm scope of the work |  | CFO | bar: Week number 1
Confirm goals and objectives |  | CFO | bar: Week number 1
Develop detailed workplan including stakeholder analysis and communication plan |  | Change team | bar: Week number 1 to Week number 3
Align finance leadership, business leadership and the finance team with the same vision | TOOL 5 LEADERSHIP ALIGNMENT | Change team | bar: Week number 1 to Week number 5
Agree governance processes and reporting |  | Change team | bar: Week number 1 to Week number 3
2. Insight |  |  | Week number 4: Phase 2
Assess current employee perceptions | TOOL 1 CULTURE SURVEY | Change team | bar: Week number 4 to Week number 9
Assess current culture and its level of maturity | TOOL 2 CULTURE MATURITY MAP | Change team | bar: Week number 4 to Week number 9
Assess current readiness for change | TOOL 3 CHANGE READINESS ASSESSMENT | Change team | bar: Week number 4 to Week number 9
Assess level of engagement of stakeholders | TOOL 6 STAKEHOLDER ANALYSIS AND CHANGE MANAGEMENT | Change team | bar: Week number 4 to Week number 9
Hold finance sub-function workshops to establish current state and any barriers to change |  | Change team | bar: Week number 5
Summarize the finance function's current state including risks, issues and enablers |  | Change team | bar: Week number 4 to Week number 8
Analysis of current state |  | Change team | bar: Week number 8 to Week number 9
3. Future state |  |  | Week number 7: Phase 3
Hold ‘future state’ workshops |  | Change team | bar: Week number 8 to Week number 14
Design revised approaches which embed sustainability into the finance function |  | Change team | bar: Week number 7 to Week number 8
Summarize new ways of working |  | Change champion | bar: Week number 9 to Week number 11
Agree future operating model that embeds sustainability |  | Change team | bar: Week number 11 to Week number 12
Incorporate into skills gap analysis of the finance function | TOOL 8 FINANCE FUNCTION SUSTAINABILITY COMPETENCIES | Everyone | bar: Week number 11 to Week number 12
Identify quick wins |  | Change champion | bar: Week number 12 to Week number 14
Complete strategic roadmap |  | Change team | bar: Week number 14
Agree business case |  | CFO | bar: Week number 14
Launch communications |  | Change team | bar: Week number 14